## Cover
PAMIT Ticket Analysis — 2026-01-01 to 2026-09-21
Generated: 2026-09-22 19:09
Source snapshot: `jira-analysis-2026-01-01-to-2026-09-21.json` · sha256 `f7f65530536a7726`
Project: PAMIT · Date range: 2026-01-01 to 2026-09-21
Total tickets: 5740 · Client tickets: 3705 · Internal: 2035
Open / Closed classification. Every status is mapped by the owner's status lists, case-insensitively. A status in neither list is reported as Unmapped and is never guessed into a bucket, so each bifurcated table carries its own Unmapped column and Total Count = Open Total + Closed Total + Unmapped. 137 of 5740 tickets (2.4%) are unmapped — see the final section.

## 1. Summary
Metric | Count
Total tickets | 5740
Client tickets | 3705 (64.5%)
Internal tickets | 2035 (35.5%)
Open | 1466 (25.5%)
Closed | 4137 (72.1%)
Unmapped status | 137 (2.4%)
Duplicates | 79 (1.4%)

## 2. Status Distribution
Status | Class | Count | % of Total
Closed | Closed | 3860 | 67.2%
Open | Open | 560 | 9.8%
Awaiting Response | Open | 406 | 7.1%
Development Analysis | Open | 212 | 3.7%
Client Release | Closed | 175 | 3%
Duplicate | Unmapped | 79 | 1.4%
Rejected | Closed | 77 | 1.3%
Business Analysis | Open | 76 | 1.3%
RCA/Resolution Review | Unmapped | 50 | 0.9%
Under Observation (No Code Change) | Open | 46 | 0.8%
Awaiting Session | Open | 32 | 0.6%
QA Testing | Open | 25 | 0.4%
Patch Shared | Open | 16 | 0.3%
Audit | Open | 16 | 0.3%
Reopen | Open | 15 | 0.3%
Development | Open | 14 | 0.2%
Ready For Released | Closed | 13 | 0.2%
Dev Review and Testing | Open | 12 | 0.2%
Solution Analysis | Open | 10 | 0.2%
Security Check | Open | 9 | 0.2%
Product Hold | Open | 8 | 0.1%
Document Review | Closed | 8 | 0.1%
Development Review | Unmapped | 7 | 0.1%
Documentation | Closed | 4 | 0.1%
Patch Developed | Open | 4 | 0.1%
Functional Testing | Open | 2 | 0%
Forward Merge | Open | 1 | 0%
RCA Rejection | Unmapped | 1 | 0%
In Progress | Open | 1 | 0%
Pending from DevOps | Open | 1 | 0%
Total |  | 5740 | 100%

## 3. Issue Type Distribution
Issue Type | Count | % of Total
Bug | 2907 | 50.6%
Sub-task | 867 | 15.1%
Task | 756 | 13.2%
Story | 472 | 8.2%
Security Fix | 364 | 6.3%
APEM Tool | 232 | 4%
Performance | 91 | 1.6%
Document | 28 | 0.5%
Client-Support | 12 | 0.2%
Epic | 4 | 0.1%
POC | 4 | 0.1%
Test Case | 3 | 0.1%
Total | 5740 | 100%

## 4. Priority Distribution
Priority | Total Count | Open |  |  | Closed |  |  | Unmapped
|  | Client | Internal | Total | Client | Internal | Total
High | 2907 | 442 | 294 | 736 | 1601 | 515 | 2116 | 55
ShowStopper | 1236 | 262 | 39 | 301 | 837 | 80 | 917 | 18
Medium | 826 | 67 | 169 | 236 | 253 | 297 | 550 | 40
Low | 771 | 42 | 151 | 193 | 141 | 413 | 554 | 24
Total | 5740 | 813 | 653 | 1466 | 2832 | 1305 | 4137 | 137

## 5. Severity Distribution
Severity | Total Count | Open |  |  | Closed |  |  | Unmapped
|  | Client | Internal | Total | Client | Internal | Total
Not set | 5553 | 769 | 617 | 1386 | 2757 | 1276 | 4033 | 134
Sev-1 | 82 | 21 | 20 | 41 | 24 | 15 | 39 | 2
Sev-2 | 50 | 9 | 7 | 16 | 27 | 6 | 33 | 1
Sev-0 | 34 | 9 | 8 | 17 | 14 | 3 | 17 | 0
Sev-3 | 21 | 5 | 1 | 6 | 10 | 5 | 15 | 0
Total | 5740 | 813 | 653 | 1466 | 2832 | 1305 | 4137 | 137

## 6A. Component — Total, Open and
Component | Total Count | Open | Closed | Unmapped
Connector | 1059 | 293 | 733 | 33
ACMO | 855 | 248 | 583 | 24
Server Manager | 629 | 173 | 437 | 19
(No component) | 456 | 53 | 387 | 16
All Modules | 446 | 143 | 296 | 7
Password Vault | 301 | 67 | 227 | 7
Arcon Service / Agent | 249 | 46 | 196 | 7
APEM Tool | 223 | 20 | 200 | 3
Settings | 212 | 74 | 136 | 2
Report / Dashboard | 207 | 61 | 140 | 6
PAM API | 201 | 70 | 127 | 4
AGW | 176 | 41 | 133 | 2
VA | 141 | 25 | 116 | 0
Password | 125 | 31 | 92 | 2
PAM - MAC Thick Client | 78 | 23 | 52 | 3
Knight Analytics | 67 | 23 | 44 | 0
SSO | 63 | 16 | 46 | 1
Workflow | 61 | 25 | 34 | 2
Linux Thick Client | 56 | 11 | 44 | 1
Application & Audit Logs | 50 | 16 | 32 | 2
UAG | 47 | 14 | 32 | 1
RTSM | 37 | 13 | 23 | 1
Research | 35 | 9 | 26 | 0
mac | 35 | 3 | 32 | 0
Access Control | 33 | 10 | 23 | 0
PYCLI | 30 | 10 | 20 | 0
Browser Plugin | 25 | 7 | 18 | 0
Digital Vault | 23 | 5 | 17 | 1
User Discovery | 21 | 8 | 13 | 0
PAM MS API | 20 | 10 | 9 | 1
Performance | 20 | 6 | 14 | 0
Administrative Console | 19 | 13 | 6 | 0
Integration | 19 | 12 | 7 | 0
PAM Lite | 19 | 6 | 11 | 2
SCIM API | 17 | 4 | 12 | 1
Auto onboarding | 15 | 7 | 8 | 0
Mobile Application | 10 | 4 | 5 | 1
Build and Deploy | 9 | 3 | 6 | 0
EPM | 9 | 3 | 6 | 0
MySQl Database | 9 | 6 | 3 | 0
Component | 8 | 2 | 5 | 1
UI | 6 | 3 | 3 | 0
RA | 5 | 0 | 4 | 1
RPA | 4 | 0 | 4 | 0
CI | 3 | 0 | 2 | 1
Cloud | 3 | 2 | 1 | 0
mfa | 3 | 2 | 1 | 0
FT - Optimising the AGW | 2 | 0 | 2 | 0
ACMO CLI | 1 | 0 | 1 | 0
Identity Access Management | 1 | 0 | 1 | 0
RPA-RND | 1 | 0 | 1 | 0
SCM | 1 | 1 | 0 | 0
Total (distinct tickets) | 5740 | 1466 | 4137 | 137

## 6B. Component — Client and Inte
Component | Total Count | Open |  |  | Closed |  |  | Unmapped
|  | Client | Internal | Total | Client | Internal | Total
Connector | 1059 | 177 | 116 | 293 | 571 | 162 | 733 | 33
ACMO | 855 | 116 | 132 | 248 | 425 | 158 | 583 | 24
Server Manager | 629 | 110 | 63 | 173 | 312 | 125 | 437 | 19
(No component) | 456 | 21 | 32 | 53 | 102 | 285 | 387 | 16
All Modules | 446 | 59 | 84 | 143 | 196 | 100 | 296 | 7
Password Vault | 301 | 44 | 23 | 67 | 169 | 58 | 227 | 7
Arcon Service / Agent | 249 | 26 | 20 | 46 | 132 | 64 | 196 | 7
APEM Tool | 223 | 15 | 5 | 20 | 188 | 12 | 200 | 3
Settings | 212 | 39 | 35 | 74 | 85 | 51 | 136 | 2
Report / Dashboard | 207 | 40 | 21 | 61 | 101 | 39 | 140 | 6
PAM API | 201 | 34 | 36 | 70 | 105 | 22 | 127 | 4
AGW | 176 | 20 | 21 | 41 | 106 | 27 | 133 | 2
VA | 141 | 24 | 1 | 25 | 116 | 0 | 116 | 0
Password | 125 | 26 | 5 | 31 | 71 | 21 | 92 | 2
PAM - MAC Thick Client | 78 | 8 | 15 | 23 | 27 | 25 | 52 | 3
Knight Analytics | 67 | 12 | 11 | 23 | 6 | 38 | 44 | 0
SSO | 63 | 14 | 2 | 16 | 41 | 5 | 46 | 1
Workflow | 61 | 21 | 4 | 25 | 29 | 5 | 34 | 2
Linux Thick Client | 56 | 5 | 6 | 11 | 23 | 21 | 44 | 1
Application & Audit Logs | 50 | 10 | 6 | 16 | 22 | 10 | 32 | 2
UAG | 47 | 7 | 7 | 14 | 25 | 7 | 32 | 1
RTSM | 37 | 7 | 6 | 13 | 13 | 10 | 23 | 1
Research | 35 | 1 | 8 | 9 | 0 | 26 | 26 | 0
mac | 35 | 3 | 0 | 3 | 26 | 6 | 32 | 0
Access Control | 33 | 2 | 8 | 10 | 11 | 12 | 23 | 0
PYCLI | 30 | 4 | 6 | 10 | 13 | 7 | 20 | 0
Browser Plugin | 25 | 4 | 3 | 7 | 15 | 3 | 18 | 0
Digital Vault | 23 | 0 | 5 | 5 | 3 | 14 | 17 | 1
User Discovery | 21 | 6 | 2 | 8 | 7 | 6 | 13 | 0
PAM MS API | 20 | 4 | 6 | 10 | 7 | 2 | 9 | 1
Performance | 20 | 5 | 1 | 6 | 14 | 0 | 14 | 0
Administrative Console | 19 | 2 | 11 | 13 | 2 | 4 | 6 | 0
Integration | 19 | 9 | 3 | 12 | 5 | 2 | 7 | 0
PAM Lite | 19 | 5 | 1 | 6 | 10 | 1 | 11 | 2
SCIM API | 17 | 3 | 1 | 4 | 6 | 6 | 12 | 1
Auto onboarding | 15 | 5 | 2 | 7 | 7 | 1 | 8 | 0
Mobile Application | 10 | 0 | 4 | 4 | 5 | 0 | 5 | 1
Build and Deploy | 9 | 0 | 3 | 3 | 2 | 4 | 6 | 0
EPM | 9 | 1 | 2 | 3 | 3 | 3 | 6 | 0
MySQl Database | 9 | 6 | 0 | 6 | 3 | 0 | 3 | 0
Component | 8 | 2 | 0 | 2 | 5 | 0 | 5 | 1
UI | 6 | 2 | 1 | 3 | 0 | 3 | 3 | 0
RA | 5 | 0 | 0 | 0 | 2 | 2 | 4 | 1
RPA | 4 | 0 | 0 | 0 | 1 | 3 | 4 | 0
CI | 3 | 0 | 0 | 0 | 1 | 1 | 2 | 1
Cloud | 3 | 2 | 0 | 2 | 1 | 0 | 1 | 0
mfa | 3 | 1 | 1 | 2 | 1 | 0 | 1 | 0
FT - Optimising the AGW | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0
ACMO CLI | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0
Identity Access Management | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0
RPA-RND | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0
SCM | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0
Total (distinct tickets) | 5740 | 813 | 653 | 1466 | 2832 | 1305 | 4137 | 137

## 7. Top Reporters (Top 20)
Reporter | Count | % of Total
Kunal Parwal | 593 | 10.3%
Shankar Chabukswar | 293 | 5.1%
Zuber Tivale | 255 | 4.4%
nancy.singh | 213 | 3.7%
Jeetendra Choudhary | 201 | 3.5%
Anagha | 194 | 3.4%
Sushma Battula | 192 | 3.3%
Yash Kharkar | 190 | 3.3%
Atharva Pawar | 121 | 2.1%
Khushhal Pal | 110 | 1.9%
Soumya Jyoti Das | 110 | 1.9%
Krutish Bhandari | 104 | 1.8%
Rohan Patil | 93 | 1.6%
Sayali Gaikwad | 93 | 1.6%
Sayali Kamble | 81 | 1.4%
Kevin Haria | 76 | 1.3%
Somesh Hinduja | 72 | 1.3%
Akshata Zore | 66 | 1.1%
Owais Ansari | 64 | 1.1%
Tanvir Ansari | 63 | 1.1%
Total (top 20 shown) | 3184 | 55.5%

## 8. Top Assignees (Top 20)
Assignee | Count | % of Total
Soumya Jyoti Das | 376 | 6.6%
Shravankumar Sharma | 317 | 5.5%
Anand Vishwakarma | 254 | 4.4%
Yash Ramani | 212 | 3.7%
Swapna Harriharan | 209 | 3.6%
Tejal Solanki | 192 | 3.3%
Shankar Chabukswar | 189 | 3.3%
Shailesh Shinde | 179 | 3.1%
Somesh Hinduja | 179 | 3.1%
Zuber Tivale | 159 | 2.8%
nancy.singh | 128 | 2.2%
Sushma Battula | 126 | 2.2%
Yuktee Sahu | 120 | 2.1%
Jeetendra Choudhary | 115 | 2%
Yash Kharkar | 114 | 2%
Anagha | 103 | 1.8%
Khushhal Pal | 74 | 1.3%
Kevin Haria | 74 | 1.3%
Anuja Pradhan | 73 | 1.3%
Vijayashree Shetty | 71 | 1.2%
Total (top 20 shown) | 3264 | 56.9%

## 9. Monthly Creation Trend
Month | Total | Client | % Client
2026-01 | 810 | 463 | 57.2%
2026-02 | 623 | 442 | 70.9%
2026-03 | 852 | 456 | 53.5%
2026-04 | 644 | 440 | 68.3%
2026-05 | 494 | 387 | 78.3%
2026-06 | 675 | 468 | 69.3%
2026-07 | 679 | 399 | 58.8%
2026-08 | 606 | 404 | 66.7%
2026-09 | 357 | 246 | 68.9%
Total | 5740 | 3705 | 64.5%

## 10. Weekly Creation Trend
Week | Count
2026-W01 | 38
2026-W02 | 203
2026-W03 | 136
2026-W04 | 257
2026-W05 | 178
2026-W06 | 143
2026-W07 | 172
2026-W08 | 154
2026-W09 | 157
2026-W10 | 144
2026-W11 | 172
2026-W12 | 272
2026-W13 | 201
2026-W14 | 117
2026-W15 | 134
2026-W16 | 202
2026-W17 | 161
2026-W18 | 92
2026-W19 | 132
2026-W20 | 138
2026-W21 | 99
2026-W22 | 121
2026-W23 | 141
2026-W24 | 128
2026-W25 | 162
2026-W26 | 152
2026-W27 | 200
2026-W28 | 123
2026-W29 | 138
2026-W30 | 170
2026-W31 | 142
2026-W32 | 158
2026-W33 | 159
2026-W34 | 153
2026-W35 | 102
2026-W36 | 127
2026-W37 | 136
2026-W38 | 82
2026-W39 | 44
Total | 5740

## 11. Fix Version Distribution
Fix Version | Count
35.8.29 HF6 | 241
35.8.29 HF7 | 152
35.8.29 HF12 | 120
35.8.29 HF5 | 107
35.8.29 HF10 | 105
35.8.29 HF8 | 93
35.8.29 HF14 | 90
35.8.29 HF15 | 83
35.8.29 HF13 | 82
35.8.29 HF3 | 70
35.8.29 HF4 | 64
35.8.29 HF11 | 62
35.8.29 HF9 | 37
Backlog | 35
35.8.29 HF11 P2 | 33
35.8.27 | 22
35.8.29 HF2 | 18
35.8.29 HF1 | 17
35.8.24 HF14 | 15
35.8.28 | 11
35.8.29 HF16 | 11
MAC 12.9.0.0 | 10
35.8.29 HF9 Patch1 | 10
35.8.29 HF11 P3 | 9
35.8.29 | 8
Backlog Awaiting Response | 8
35.8.13 HF22 | 7
35.8.24 HF13.1 | 6
35.8.24 HF13 | 4
35.8.18 HF10 | 4
Total (top 30 shown) | 1534

## 12. Affected Milestone Distribu
Affected Milestone | Count
35.8.29 HF6 | 579
35.8.29 HF5 | 342
35.8.29 HF1 | 337
35.8.29 HF11 | 318
35.8.29 HF2 | 309
35.8.28 | 270
35.8.29 HF7 | 220
35.8.29 HF9 | 193
35.8.29 HF3 | 166
35.8.27 | 125
35.8.29 HF10 | 110
35.8.29 HF12 | 99
35.8.24 | 96
35.8.24 HF11 | 89
4.8.5.0_U16SP2_B35.8.21 | 88
35.8.24 HF6 | 74
35.8.29 HF13 | 69
35.8.24 HF8 | 66
4.8.5.0_U16SP2_B35.8.13 | 61
35.8.29 HF4 | 60
4.8.5.0_U16SP2_B35.8.20 | 58
35.8.29 HF8 | 58
35.8.24 HF13 | 57
4.8.5.0_U16SP2_B35.8.16 | 56
35.8.24 HF3 | 50
U16 SP2 35.6 | 49
4.8.5.0_U16SP2_B35.8.18 | 40
4.8.5.0_U16_HF8 | 35
35.8.29 | 32
35.8.24 HF7 | 32
Total (top 30 shown) | 4138

## 13. Root Cause Analysis (RCA)
RCA | Count | % of Total
Not set | 1807 | 31.5%
Others - Resolved Issue | 617 | 10.7%
Code - Logic Issue | 533 | 9.3%
Requests - Enhancement | 469 | 8.2%
Environment - Misconfiguration | 345 | 6%
Others - Working as expected | 256 | 4.5%
Requests - APEM Tool | 189 | 3.3%
Analysis - Inadequate Technical Design | 182 | 3.2%
Environment - 3rd Party compatibility | 140 | 2.4%
Documentation - Administrator / User Guide | 134 | 2.3%
Environment- Env unavailable | 133 | 2.3%
Environment - Non replicated | 119 | 2.1%
Not a bug | 93 | 1.6%
Code - Incorrect Standards | 91 | 1.6%
Code - Security Issue | 91 | 1.6%
Code - Performance Issue | 64 | 1.1%
Analysis - Inadequate Test Coverage | 56 | 1%
Code - Packaging Issue | 55 | 1%
Requests - Information Request | 50 | 0.9%
Missing Code / DB Scripts | 41 | 0.7%
Total (top 20 shown) | 5465 | 95.2%

## 14. Hosting Environment
Hosting Environment | Count | % of Total
Not set | 4430 | 77.2%
Windows | 1280 | 22.3%
RHEL | 18 | 0.3%
Ubuntu | 12 | 0.2%
Total | 5740 | 100%

## 15. Module
Module | Count | % of Total
Not set | 5740 | 100%
Total | 5740 | 100%

## 16. Category
Category | Count | % of Total
Not set | 5735 | 99.9%
Connector | 3 | 0.1%
Cloud | 1 | 0%
All Modules | 1 | 0%
Total | 5740 | 100%

## 17. Client vs Internal by Issue
Issue Type | Client | Internal | Total
APEM Tool | 221 | 11 | 232
Bug | 2307 | 600 | 2907
Client-Support | 12 | 0 | 12
Document | 27 | 1 | 28
Epic | 2 | 2 | 4
POC | 2 | 2 | 4
Performance | 84 | 7 | 91
Security Fix | 311 | 53 | 364
Story | 313 | 159 | 472
Sub-task | 98 | 769 | 867
Task | 326 | 430 | 756
Test Case | 2 | 1 | 3
Total | 3705 | 2035 | 5740

## 18. Client vs Internal by Statu
Status | Client | Internal | Total
Audit | 14 | 2 | 16
Awaiting Response | 334 | 72 | 406
Awaiting Session | 31 | 1 | 32
Business Analysis | 53 | 23 | 76
Client Release | 102 | 73 | 175
Closed | 2653 | 1207 | 3860
Dev Review and Testing | 4 | 8 | 12
Development | 4 | 10 | 14
Development Analysis | 142 | 70 | 212
Development Review | 3 | 4 | 7
Document Review | 7 | 1 | 8
Documentation | 1 | 3 | 4
Duplicate | 56 | 23 | 79
Forward Merge | 1 | 0 | 1
Functional Testing | 0 | 2 | 2
In Progress | 1 | 0 | 1
Open | 131 | 429 | 560
Patch Developed | 4 | 0 | 4
Patch Shared | 13 | 3 | 16
Pending from DevOps | 1 | 0 | 1
Product Hold | 6 | 2 | 8
QA Testing | 18 | 7 | 25
RCA Rejection | 1 | 0 | 1
RCA/Resolution Review | 0 | 50 | 50
Ready For Released | 9 | 4 | 13
Rejected | 60 | 17 | 77
Reopen | 3 | 12 | 15
Security Check | 3 | 6 | 9
Solution Analysis | 7 | 3 | 10
Under Observation (No Code Change) | 43 | 3 | 46
Total | 3705 | 2035 | 5740

## 19. Open Tickets by Priority
Priority | Open Count
High | 736
ShowStopper | 301
Medium | 236
Low | 193
Total | 1466

## 21. High-Priority Open Tickets
Key | Summary | Status | Priority | Assignee
PAMIT-36957 | ICICI Bank |  | VA: Disable non-essential HTTP Methods. | Awaiting Response
PAMIT-37001 | Discrepancy in User Status Report for MSSQL | Awaiting Response | High | Girish Nhavkar
PAMIT-37027 | NTPC | Knight Analytics Unable to load Daily Detection Report & User Report | Awaiting Response | High
PAMIT-37031 | KB: KB Updations | Open | High | Former user
PAMIT-37061 | KB: PAM API: Services are not getting mapped to users when onboarding through AP | Open | High | Jeetendra Choudhary
PAMIT-37096 | ICICI Bank U16SP2 |  | User details API error | Awaiting Response
PAMIT-37106 | ICICI Bank U16SP2 |  | Service details API error | Under Observation (No Code Change)
PAMIT-37108 | ICICI Bank U16SP2 |  | User registration API error | Awaiting Response
PAMIT-37148 | IndusInd Bank |  | issue in ARCON PAM Logs in SM
PAMIT-37151 | IndusInd Bank |  | Issue in User & service mapping report
PAMIT-37219 | KB: Connector: Incorrect MAC Received error when trying to access server with Ar | Open | High | Sarfraj Sayyad
PAMIT-37224 | ITD-SHAPK |  | New Connector Request Winbox for windows | Development Analysis
PAMIT-37260 | KB: ACMO: Some Users Unable to Login After DB Upgrade due to config change done | Open | High | Rohan Patil
PAMIT-37286 | PPFAS |  | New connector Table Plus for connecting to RDS DB via client's internal | Awaiting Response
PAMIT-37293 | PAM_MOBILE_APP_1.0.16 Package Tesing : After attempting to login user is redirec | Open | High | Dhaval Mange
PAMIT-37294 | RTSM session is present on ACMO --> SSM --> RTSM despite Real Time Session Monit | Awaiting Response | High | Dipti Gokhale
PAMIT-37298 | PAMAPI, VaultAPI, AWSAPI VA - LOG4Net , Restsharp library update | Open | High | Trupti A Shirdhankar
PAMIT-37310 | Star Health | Issue with the Video logs | Under Observation (No Code Change) | High
PAMIT-37356 | ICICI Bank |  | Revalidate the VA for U16SP2 35.8.13 latest HF | Awaiting Response
PAMIT-37401 | CLONE - RSPCA |  | UTC not working | Awaiting Response
PAMIT-37409 | IndusInd bank |  | EPM requirement
PAMIT-37435 | CLONE - PSS PAM | RDP/SSH/AWB SSO not working for Windows Machines with Arabic P | Open | ShowStopper
PAMIT-37449 | FT - Reports Graph should display data for total records | Business Analysis | ShowStopper | Anand Vishwakarma
PAMIT-37479 | RBI |  | Incorrect DATA exporting in User request workflow approver request from A | Awaiting Response
PAMIT-37536 | KB: Connector: Issue Accessing TOAD for Oracle via PAM due to incorrect JSON con | Open | High | Siddhant Patkar
PAMIT-37537 | KB: Video Logs: Issue While Viewing Video Logs – Object Reference Error due to i | Open | High | Arul Pavithran
PAMIT-37546 | Converting Video Logs Pending,Approve,Reject in MYSQL | Development Analysis | High | Bansi Ghanva
PAMIT-37547 | Reg: Video logs not able to play | Awaiting Session | High | srikanth.rendla
PAMIT-37617 | Reg: Video logs not able to play | Awaiting Response | High | srikanth.rendla
PAMIT-37733 | ICICI Bank U16SP2 |  | User discovery MSSQL protocol type error | Awaiting Session

## 23. Unmapped Status Review
Status | Client | Internal | Total
Duplicate | 56 | 23 | 79
RCA/Resolution Review | 0 | 50 | 50
Development Review | 3 | 4 | 7
RCA Rejection | 1 | 0 | 1
Total | 60 | 77 | 137

## All Data
1. Summary
Metric | Count
Total tickets | 5740
Client tickets | 3705 (64.5%)
Internal tickets | 2035 (35.5%)
Open | 1466 (25.5%)
Closed | 4137 (72.1%)
Unmapped status | 137 (2.4%)
Duplicates | 79 (1.4%)
2. Status Distribution
Status | Class | Count | % of Total
Closed | Closed | 3860 | 67.2%
Open | Open | 560 | 9.8%
Awaiting Response | Open | 406 | 7.1%
Development Analysis | Open | 212 | 3.7%
Client Release | Closed | 175 | 3%
Duplicate | Unmapped | 79 | 1.4%
Rejected | Closed | 77 | 1.3%
Business Analysis | Open | 76 | 1.3%
RCA/Resolution Review | Unmapped | 50 | 0.9%
Under Observation (No Code Change) | Open | 46 | 0.8%
Awaiting Session | Open | 32 | 0.6%
QA Testing | Open | 25 | 0.4%
Patch Shared | Open | 16 | 0.3%
Audit | Open | 16 | 0.3%
Reopen | Open | 15 | 0.3%
Development | Open | 14 | 0.2%
Ready For Released | Closed | 13 | 0.2%
Dev Review and Testing | Open | 12 | 0.2%
Solution Analysis | Open | 10 | 0.2%
Security Check | Open | 9 | 0.2%
Product Hold | Open | 8 | 0.1%
Document Review | Closed | 8 | 0.1%
Development Review | Unmapped | 7 | 0.1%
Documentation | Closed | 4 | 0.1%
Patch Developed | Open | 4 | 0.1%
Functional Testing | Open | 2 | 0%
Forward Merge | Open | 1 | 0%
RCA Rejection | Unmapped | 1 | 0%
In Progress | Open | 1 | 0%
Pending from DevOps | Open | 1 | 0%
Total |  | 5740 | 100%
3. Issue Type Distribution
Issue Type | Count | % of Total
Bug | 2907 | 50.6%
Sub-task | 867 | 15.1%
Task | 756 | 13.2%
Story | 472 | 8.2%
Security Fix | 364 | 6.3%
APEM Tool | 232 | 4%
Performance | 91 | 1.6%
Document | 28 | 0.5%
Client-Support | 12 | 0.2%
Epic | 4 | 0.1%
POC | 4 | 0.1%
Test Case | 3 | 0.1%
Total | 5740 | 100%
4. Priority Distribution
Priority | Total Count | Open |  |  | Closed |  |  | Unmapped
|  | Client | Internal | Total | Client | Internal | Total
High | 2907 | 442 | 294 | 736 | 1601 | 515 | 2116 | 55
ShowStopper | 1236 | 262 | 39 | 301 | 837 | 80 | 917 | 18
Medium | 826 | 67 | 169 | 236 | 253 | 297 | 550 | 40
Low | 771 | 42 | 151 | 193 | 141 | 413 | 554 | 24
Total | 5740 | 813 | 653 | 1466 | 2832 | 1305 | 4137 | 137
5. Severity Distribution
Severity | Total Count | Open |  |  | Closed |  |  | Unmapped
|  | Client | Internal | Total | Client | Internal | Total
Not set | 5553 | 769 | 617 | 1386 | 2757 | 1276 | 4033 | 134
Sev-1 | 82 | 21 | 20 | 41 | 24 | 15 | 39 | 2
Sev-2 | 50 | 9 | 7 | 16 | 27 | 6 | 33 | 1
Sev-0 | 34 | 9 | 8 | 17 | 14 | 3 | 17 | 0
Sev-3 | 21 | 5 | 1 | 6 | 10 | 5 | 15 | 0
Total | 5740 | 813 | 653 | 1466 | 2832 | 1305 | 4137 | 137
6A. Component — Total, Open and Closed
Component | Total Count | Open | Closed | Unmapped
Connector | 1059 | 293 | 733 | 33
ACMO | 855 | 248 | 583 | 24
Server Manager | 629 | 173 | 437 | 19
(No component) | 456 | 53 | 387 | 16
All Modules | 446 | 143 | 296 | 7
Password Vault | 301 | 67 | 227 | 7
Arcon Service / Agent | 249 | 46 | 196 | 7
APEM Tool | 223 | 20 | 200 | 3
Settings | 212 | 74 | 136 | 2
Report / Dashboard | 207 | 61 | 140 | 6
PAM API | 201 | 70 | 127 | 4
AGW | 176 | 41 | 133 | 2
VA | 141 | 25 | 116 | 0
Password | 125 | 31 | 92 | 2
PAM - MAC Thick Client | 78 | 23 | 52 | 3
Knight Analytics | 67 | 23 | 44 | 0
SSO | 63 | 16 | 46 | 1
Workflow | 61 | 25 | 34 | 2
Linux Thick Client | 56 | 11 | 44 | 1
Application & Audit Logs | 50 | 16 | 32 | 2
UAG | 47 | 14 | 32 | 1
RTSM | 37 | 13 | 23 | 1
Research | 35 | 9 | 26 | 0
mac | 35 | 3 | 32 | 0
Access Control | 33 | 10 | 23 | 0
PYCLI | 30 | 10 | 20 | 0
Browser Plugin | 25 | 7 | 18 | 0
Digital Vault | 23 | 5 | 17 | 1
User Discovery | 21 | 8 | 13 | 0
PAM MS API | 20 | 10 | 9 | 1
Performance | 20 | 6 | 14 | 0
Administrative Console | 19 | 13 | 6 | 0
Integration | 19 | 12 | 7 | 0
PAM Lite | 19 | 6 | 11 | 2
SCIM API | 17 | 4 | 12 | 1
Auto onboarding | 15 | 7 | 8 | 0
Mobile Application | 10 | 4 | 5 | 1
Build and Deploy | 9 | 3 | 6 | 0
EPM | 9 | 3 | 6 | 0
MySQl Database | 9 | 6 | 3 | 0
Component | 8 | 2 | 5 | 1
UI | 6 | 3 | 3 | 0
RA | 5 | 0 | 4 | 1
RPA | 4 | 0 | 4 | 0
CI | 3 | 0 | 2 | 1
Cloud | 3 | 2 | 1 | 0
mfa | 3 | 2 | 1 | 0
FT - Optimising the AGW | 2 | 0 | 2 | 0
ACMO CLI | 1 | 0 | 1 | 0
Identity Access Management | 1 | 0 | 1 | 0
RPA-RND | 1 | 0 | 1 | 0
SCM | 1 | 1 | 0 | 0
Total (distinct tickets) | 5740 | 1466 | 4137 | 137
6B. Component — Client and Internal split
Component | Total Count | Open |  |  | Closed |  |  | Unmapped
|  | Client | Internal | Total | Client | Internal | Total
Connector | 1059 | 177 | 116 | 293 | 571 | 162 | 733 | 33
ACMO | 855 | 116 | 132 | 248 | 425 | 158 | 583 | 24
Server Manager | 629 | 110 | 63 | 173 | 312 | 125 | 437 | 19
(No component) | 456 | 21 | 32 | 53 | 102 | 285 | 387 | 16
All Modules | 446 | 59 | 84 | 143 | 196 | 100 | 296 | 7
Password Vault | 301 | 44 | 23 | 67 | 169 | 58 | 227 | 7
Arcon Service / Agent | 249 | 26 | 20 | 46 | 132 | 64 | 196 | 7
APEM Tool | 223 | 15 | 5 | 20 | 188 | 12 | 200 | 3
Settings | 212 | 39 | 35 | 74 | 85 | 51 | 136 | 2
Report / Dashboard | 207 | 40 | 21 | 61 | 101 | 39 | 140 | 6
PAM API | 201 | 34 | 36 | 70 | 105 | 22 | 127 | 4
AGW | 176 | 20 | 21 | 41 | 106 | 27 | 133 | 2
VA | 141 | 24 | 1 | 25 | 116 | 0 | 116 | 0
Password | 125 | 26 | 5 | 31 | 71 | 21 | 92 | 2
PAM - MAC Thick Client | 78 | 8 | 15 | 23 | 27 | 25 | 52 | 3
Knight Analytics | 67 | 12 | 11 | 23 | 6 | 38 | 44 | 0
SSO | 63 | 14 | 2 | 16 | 41 | 5 | 46 | 1
Workflow | 61 | 21 | 4 | 25 | 29 | 5 | 34 | 2
Linux Thick Client | 56 | 5 | 6 | 11 | 23 | 21 | 44 | 1
Application & Audit Logs | 50 | 10 | 6 | 16 | 22 | 10 | 32 | 2
UAG | 47 | 7 | 7 | 14 | 25 | 7 | 32 | 1
RTSM | 37 | 7 | 6 | 13 | 13 | 10 | 23 | 1
Research | 35 | 1 | 8 | 9 | 0 | 26 | 26 | 0
mac | 35 | 3 | 0 | 3 | 26 | 6 | 32 | 0
Access Control | 33 | 2 | 8 | 10 | 11 | 12 | 23 | 0
PYCLI | 30 | 4 | 6 | 10 | 13 | 7 | 20 | 0
Browser Plugin | 25 | 4 | 3 | 7 | 15 | 3 | 18 | 0
Digital Vault | 23 | 0 | 5 | 5 | 3 | 14 | 17 | 1
User Discovery | 21 | 6 | 2 | 8 | 7 | 6 | 13 | 0
PAM MS API | 20 | 4 | 6 | 10 | 7 | 2 | 9 | 1
Performance | 20 | 5 | 1 | 6 | 14 | 0 | 14 | 0
Administrative Console | 19 | 2 | 11 | 13 | 2 | 4 | 6 | 0
Integration | 19 | 9 | 3 | 12 | 5 | 2 | 7 | 0
PAM Lite | 19 | 5 | 1 | 6 | 10 | 1 | 11 | 2
SCIM API | 17 | 3 | 1 | 4 | 6 | 6 | 12 | 1
Auto onboarding | 15 | 5 | 2 | 7 | 7 | 1 | 8 | 0
Mobile Application | 10 | 0 | 4 | 4 | 5 | 0 | 5 | 1
Build and Deploy | 9 | 0 | 3 | 3 | 2 | 4 | 6 | 0
EPM | 9 | 1 | 2 | 3 | 3 | 3 | 6 | 0
MySQl Database | 9 | 6 | 0 | 6 | 3 | 0 | 3 | 0
Component | 8 | 2 | 0 | 2 | 5 | 0 | 5 | 1
UI | 6 | 2 | 1 | 3 | 0 | 3 | 3 | 0
RA | 5 | 0 | 0 | 0 | 2 | 2 | 4 | 1
RPA | 4 | 0 | 0 | 0 | 1 | 3 | 4 | 0
CI | 3 | 0 | 0 | 0 | 1 | 1 | 2 | 1
Cloud | 3 | 2 | 0 | 2 | 1 | 0 | 1 | 0
mfa | 3 | 1 | 1 | 2 | 1 | 0 | 1 | 0
FT - Optimising the AGW | 2 | 0 | 0 | 0 | 2 | 0 | 2 | 0
ACMO CLI | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0
Identity Access Management | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0
RPA-RND | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0
SCM | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0
Total (distinct tickets) | 5740 | 813 | 653 | 1466 | 2832 | 1305 | 4137 | 137
7. Top Reporters (Top 20)
Reporter | Count | % of Total
Kunal Parwal | 593 | 10.3%
Shankar Chabukswar | 293 | 5.1%
Zuber Tivale | 255 | 4.4%
nancy.singh | 213 | 3.7%
Jeetendra Choudhary | 201 | 3.5%
Anagha | 194 | 3.4%
Sushma Battula | 192 | 3.3%
Yash Kharkar | 190 | 3.3%
Atharva Pawar | 121 | 2.1%
Khushhal Pal | 110 | 1.9%
Soumya Jyoti Das | 110 | 1.9%
Krutish Bhandari | 104 | 1.8%
Rohan Patil | 93 | 1.6%
Sayali Gaikwad | 93 | 1.6%
Sayali Kamble | 81 | 1.4%
Kevin Haria | 76 | 1.3%
Somesh Hinduja | 72 | 1.3%
Akshata Zore | 66 | 1.1%
Owais Ansari | 64 | 1.1%
Tanvir Ansari | 63 | 1.1%
Total (top 20 shown) | 3184 | 55.5%
8. Top Assignees (Top 20)
Assignee | Count | % of Total
Soumya Jyoti Das | 376 | 6.6%
Shravankumar Sharma | 317 | 5.5%
Anand Vishwakarma | 254 | 4.4%
Yash Ramani | 212 | 3.7%
Swapna Harriharan | 209 | 3.6%
Tejal Solanki | 192 | 3.3%
Shankar Chabukswar | 189 | 3.3%
Shailesh Shinde | 179 | 3.1%
Somesh Hinduja | 179 | 3.1%
Zuber Tivale | 159 | 2.8%
nancy.singh | 128 | 2.2%
Sushma Battula | 126 | 2.2%
Yuktee Sahu | 120 | 2.1%
Jeetendra Choudhary | 115 | 2%
Yash Kharkar | 114 | 2%
Anagha | 103 | 1.8%
Khushhal Pal | 74 | 1.3%
Kevin Haria | 74 | 1.3%
Anuja Pradhan | 73 | 1.3%
Vijayashree Shetty | 71 | 1.2%
Total (top 20 shown) | 3264 | 56.9%
9. Monthly Creation Trend
Month | Total | Client | % Client
2026-01 | 810 | 463 | 57.2%
2026-02 | 623 | 442 | 70.9%
2026-03 | 852 | 456 | 53.5%
2026-04 | 644 | 440 | 68.3%
2026-05 | 494 | 387 | 78.3%
2026-06 | 675 | 468 | 69.3%
2026-07 | 679 | 399 | 58.8%
2026-08 | 606 | 404 | 66.7%
2026-09 | 357 | 246 | 68.9%
Total | 5740 | 3705 | 64.5%
10. Weekly Creation Trend
Week | Count
2026-W01 | 38
2026-W02 | 203
2026-W03 | 136
2026-W04 | 257
2026-W05 | 178
2026-W06 | 143
2026-W07 | 172
2026-W08 | 154
2026-W09 | 157
2026-W10 | 144
2026-W11 | 172
2026-W12 | 272
2026-W13 | 201
2026-W14 | 117
2026-W15 | 134
2026-W16 | 202
2026-W17 | 161
2026-W18 | 92
2026-W19 | 132
2026-W20 | 138
2026-W21 | 99
2026-W22 | 121
2026-W23 | 141
2026-W24 | 128
2026-W25 | 162
2026-W26 | 152
2026-W27 | 200
2026-W28 | 123
2026-W29 | 138
2026-W30 | 170
2026-W31 | 142
2026-W32 | 158
2026-W33 | 159
2026-W34 | 153
2026-W35 | 102
2026-W36 | 127
2026-W37 | 136
2026-W38 | 82
2026-W39 | 44
Total | 5740
11. Fix Version Distribution
Fix Version | Count
35.8.29 HF6 | 241
35.8.29 HF7 | 152
35.8.29 HF12 | 120
35.8.29 HF5 | 107
35.8.29 HF10 | 105
35.8.29 HF8 | 93
35.8.29 HF14 | 90
35.8.29 HF15 | 83
35.8.29 HF13 | 82
35.8.29 HF3 | 70
35.8.29 HF4 | 64
35.8.29 HF11 | 62
35.8.29 HF9 | 37
Backlog | 35
35.8.29 HF11 P2 | 33
35.8.27 | 22
35.8.29 HF2 | 18
35.8.29 HF1 | 17
35.8.24 HF14 | 15
35.8.28 | 11
35.8.29 HF16 | 11
MAC 12.9.0.0 | 10
35.8.29 HF9 Patch1 | 10
35.8.29 HF11 P3 | 9
35.8.29 | 8
Backlog Awaiting Response | 8
35.8.13 HF22 | 7
35.8.24 HF13.1 | 6
35.8.24 HF13 | 4
35.8.18 HF10 | 4
Total (top 30 shown) | 1534
12. Affected Milestone Distribution
Affected Milestone | Count
35.8.29 HF6 | 579
35.8.29 HF5 | 342
35.8.29 HF1 | 337
35.8.29 HF11 | 318
35.8.29 HF2 | 309
35.8.28 | 270
35.8.29 HF7 | 220
35.8.29 HF9 | 193
35.8.29 HF3 | 166
35.8.27 | 125
35.8.29 HF10 | 110
35.8.29 HF12 | 99
35.8.24 | 96
35.8.24 HF11 | 89
4.8.5.0_U16SP2_B35.8.21 | 88
35.8.24 HF6 | 74
35.8.29 HF13 | 69
35.8.24 HF8 | 66
4.8.5.0_U16SP2_B35.8.13 | 61
35.8.29 HF4 | 60
4.8.5.0_U16SP2_B35.8.20 | 58
35.8.29 HF8 | 58
35.8.24 HF13 | 57
4.8.5.0_U16SP2_B35.8.16 | 56
35.8.24 HF3 | 50
U16 SP2 35.6 | 49
4.8.5.0_U16SP2_B35.8.18 | 40
4.8.5.0_U16_HF8 | 35
35.8.29 | 32
35.8.24 HF7 | 32
Total (top 30 shown) | 4138
13. Root Cause Analysis (RCA)
RCA | Count | % of Total
Not set | 1807 | 31.5%
Others - Resolved Issue | 617 | 10.7%
Code - Logic Issue | 533 | 9.3%
Requests - Enhancement | 469 | 8.2%
Environment - Misconfiguration | 345 | 6%
Others - Working as expected | 256 | 4.5%
Requests - APEM Tool | 189 | 3.3%
Analysis - Inadequate Technical Design | 182 | 3.2%
Environment - 3rd Party compatibility | 140 | 2.4%
Documentation - Administrator / User Guide | 134 | 2.3%
Environment- Env unavailable | 133 | 2.3%
Environment - Non replicated | 119 | 2.1%
Not a bug | 93 | 1.6%
Code - Incorrect Standards | 91 | 1.6%
Code - Security Issue | 91 | 1.6%
Code - Performance Issue | 64 | 1.1%
Analysis - Inadequate Test Coverage | 56 | 1%
Code - Packaging Issue | 55 | 1%
Requests - Information Request | 50 | 0.9%
Missing Code / DB Scripts | 41 | 0.7%
Total (top 20 shown) | 5465 | 95.2%
14. Hosting Environment
Hosting Environment | Count | % of Total
Not set | 4430 | 77.2%
Windows | 1280 | 22.3%
RHEL | 18 | 0.3%
Ubuntu | 12 | 0.2%
Total | 5740 | 100%
15. Module
Module | Count | % of Total
Not set | 5740 | 100%
Total | 5740 | 100%
16. Category
Category | Count | % of Total
Not set | 5735 | 99.9%
Connector | 3 | 0.1%
Cloud | 1 | 0%
All Modules | 1 | 0%
Total | 5740 | 100%
17. Client vs Internal by Issue Type
Issue Type | Client | Internal | Total
APEM Tool | 221 | 11 | 232
Bug | 2307 | 600 | 2907
Client-Support | 12 | 0 | 12
Document | 27 | 1 | 28
Epic | 2 | 2 | 4
POC | 2 | 2 | 4
Performance | 84 | 7 | 91
Security Fix | 311 | 53 | 364
Story | 313 | 159 | 472
Sub-task | 98 | 769 | 867
Task | 326 | 430 | 756
Test Case | 2 | 1 | 3
Total | 3705 | 2035 | 5740
18. Client vs Internal by Status
Status | Client | Internal | Total
Audit | 14 | 2 | 16
Awaiting Response | 334 | 72 | 406
Awaiting Session | 31 | 1 | 32
Business Analysis | 53 | 23 | 76
Client Release | 102 | 73 | 175
Closed | 2653 | 1207 | 3860
Dev Review and Testing | 4 | 8 | 12
Development | 4 | 10 | 14
Development Analysis | 142 | 70 | 212
Development Review | 3 | 4 | 7
Document Review | 7 | 1 | 8
Documentation | 1 | 3 | 4
Duplicate | 56 | 23 | 79
Forward Merge | 1 | 0 | 1
Functional Testing | 0 | 2 | 2
In Progress | 1 | 0 | 1
Open | 131 | 429 | 560
Patch Developed | 4 | 0 | 4
Patch Shared | 13 | 3 | 16
Pending from DevOps | 1 | 0 | 1
Product Hold | 6 | 2 | 8
QA Testing | 18 | 7 | 25
RCA Rejection | 1 | 0 | 1
RCA/Resolution Review | 0 | 50 | 50
Ready For Released | 9 | 4 | 13
Rejected | 60 | 17 | 77
Reopen | 3 | 12 | 15
Security Check | 3 | 6 | 9
Solution Analysis | 7 | 3 | 10
Under Observation (No Code Change) | 43 | 3 | 46
Total | 3705 | 2035 | 5740
19. Open Tickets by Priority
Priority | Open Count
High | 736
ShowStopper | 301
Medium | 236
Low | 193
Total | 1466
21. High-Priority Open Tickets (High / ShowStopper)
Key | Summary | Status | Priority | Assignee
PAMIT-36957 | ICICI Bank |  | VA: Disable non-essential HTTP Methods. | Awaiting Response
PAMIT-37001 | Discrepancy in User Status Report for MSSQL | Awaiting Response | High | Girish Nhavkar
PAMIT-37027 | NTPC | Knight Analytics Unable to load Daily Detection Report & User Report | Awaiting Response | High
PAMIT-37031 | KB: KB Updations | Open | High | Former user
PAMIT-37061 | KB: PAM API: Services are not getting mapped to users when onboarding through AP | Open | High | Jeetendra Choudhary
PAMIT-37096 | ICICI Bank U16SP2 |  | User details API error | Awaiting Response
PAMIT-37106 | ICICI Bank U16SP2 |  | Service details API error | Under Observation (No Code Change)
PAMIT-37108 | ICICI Bank U16SP2 |  | User registration API error | Awaiting Response
PAMIT-37148 | IndusInd Bank |  | issue in ARCON PAM Logs in SM
PAMIT-37151 | IndusInd Bank |  | Issue in User & service mapping report
PAMIT-37219 | KB: Connector: Incorrect MAC Received error when trying to access server with Ar | Open | High | Sarfraj Sayyad
PAMIT-37224 | ITD-SHAPK |  | New Connector Request Winbox for windows | Development Analysis
PAMIT-37260 | KB: ACMO: Some Users Unable to Login After DB Upgrade due to config change done | Open | High | Rohan Patil
PAMIT-37286 | PPFAS |  | New connector Table Plus for connecting to RDS DB via client's internal | Awaiting Response
PAMIT-37293 | PAM_MOBILE_APP_1.0.16 Package Tesing : After attempting to login user is redirec | Open | High | Dhaval Mange
PAMIT-37294 | RTSM session is present on ACMO --> SSM --> RTSM despite Real Time Session Monit | Awaiting Response | High | Dipti Gokhale
PAMIT-37298 | PAMAPI, VaultAPI, AWSAPI VA - LOG4Net , Restsharp library update | Open | High | Trupti A Shirdhankar
PAMIT-37310 | Star Health | Issue with the Video logs | Under Observation (No Code Change) | High
PAMIT-37356 | ICICI Bank |  | Revalidate the VA for U16SP2 35.8.13 latest HF | Awaiting Response
PAMIT-37401 | CLONE - RSPCA |  | UTC not working | Awaiting Response
PAMIT-37409 | IndusInd bank |  | EPM requirement
PAMIT-37435 | CLONE - PSS PAM | RDP/SSH/AWB SSO not working for Windows Machines with Arabic P | Open | ShowStopper
PAMIT-37449 | FT - Reports Graph should display data for total records | Business Analysis | ShowStopper | Anand Vishwakarma
PAMIT-37479 | RBI |  | Incorrect DATA exporting in User request workflow approver request from A | Awaiting Response
PAMIT-37536 | KB: Connector: Issue Accessing TOAD for Oracle via PAM due to incorrect JSON con | Open | High | Siddhant Patkar
PAMIT-37537 | KB: Video Logs: Issue While Viewing Video Logs – Object Reference Error due to i | Open | High | Arul Pavithran
PAMIT-37546 | Converting Video Logs Pending,Approve,Reject in MYSQL | Development Analysis | High | Bansi Ghanva
PAMIT-37547 | Reg: Video logs not able to play | Awaiting Session | High | srikanth.rendla
PAMIT-37617 | Reg: Video logs not able to play | Awaiting Response | High | srikanth.rendla
PAMIT-37733 | ICICI Bank U16SP2 |  | User discovery MSSQL protocol type error | Awaiting Session
23. Unmapped Status Review
Status | Client | Internal | Total
Duplicate | 56 | 23 | 79
RCA/Resolution Review | 0 | 50 | 50
Development Review | 3 | 4 | 7
RCA Rejection | 1 | 0 | 1
Total | 60 | 77 | 137