## Cover
CI (Converged Identity) Ticket Analysis — 2026-01-01 to 2026-09-21
Generated: 2026-09-22 19:09
Source snapshot: `ci-analysis-2026-01-01-to-2026-09-21.json` · sha256 `5e12f6be2f084c73`
Project: CI (CI) · Date range: 2026-01-01 to 2026-09-21
Total tickets: 5994 · Client tickets: 1456 · Internal: 4538
Open / Closed classification. Every status is mapped by the owner's status lists, case-insensitively. A status in neither list is reported as Unmapped and is never guessed into a bucket, so each bifurcated table carries its own Unmapped column and Total Count = Open Total + Closed Total + Unmapped. 262 of 5994 tickets (4.4%) are unmapped.
Client / Internal. CI's internal marker is `Internal Arcon`. 825 tickets (13.8%) carry no Primary Client and are counted as Internal, per the owner's decision; they are listed in their own section so the fallback is never silent.

## 1. Summary
Metric | Count
Total tickets | 5994
Client tickets | 1456 (24.3%)
Internal tickets | 4538 (75.7%)
— of which no Primary Client | 825 (13.8%)
Sub-tasks | 1443 (24.1%)
Standalone (non-sub-task) | 4551 (75.9%)
Open | 1625 (27.1%)
Closed | 4107 (68.5%)
Unmapped status | 262 (4.4%)

## 2. Status Distribution
Status | Class | Count | % of Total
Closed | Closed | 3724 | 62.1%
Open | Open | 878 | 14.6%
Development Analysis | Open | 218 | 3.6%
Development Review | Unmapped | 170 | 2.8%
Ready For Released | Closed | 152 | 2.5%
Awaiting Response | Open | 148 | 2.5%
Rejected | Closed | 120 | 2%
Business Analysis | Open | 97 | 1.6%
Document Review | Closed | 94 | 1.6%
Duplicate | Unmapped | 82 | 1.4%
Reopen | Open | 49 | 0.8%
Audit | Open | 42 | 0.7%
Security Check | Open | 38 | 0.6%
Development | Open | 36 | 0.6%
QA Testing | Open | 29 | 0.5%
Dev Review and Testing | Open | 18 | 0.3%
Documentation | Closed | 17 | 0.3%
Patch Shared | Open | 14 | 0.2%
Solution Analysis | Open | 12 | 0.2%
Awaiting Session | Open | 11 | 0.2%
Under Observation (No Code Change) | Open | 11 | 0.2%
Patch Developed | Open | 10 | 0.2%
In Progress | Open | 5 | 0.1%
Product Hold | Open | 5 | 0.1%
Pending from DevOps | Open | 4 | 0.1%
Pre Dev Audit | Unmapped | 4 | 0.1%
Patch Tech Lead Review | Unmapped | 3 | 0.1%
Patch Passed | Unmapped | 2 | 0%
RCA/Resolution Review | Unmapped | 1 | 0%
Total |  | 5994 | 100%

## 3. Issue Type Distribution
Issue Type | Count | % of Total
Bug | 3131 | 52.2%
Sub-task | 1443 | 24.1%
Task | 735 | 12.3%
Story | 575 | 9.6%
Security Fix | 20 | 0.3%
Client-Support | 20 | 0.3%
APEM Tool | 18 | 0.3%
POC | 17 | 0.3%
Document | 16 | 0.3%
Performance | 13 | 0.2%
Test Case | 3 | 0.1%
Epic | 3 | 0.1%
Total | 5994 | 100%

## 4. Priority Distribution
Priority | Total Count | Open |  |  | Closed |  |  | Unmapped
|  | Client | Internal | Total | Client | Internal | Total
Low | 1907 | 39 | 397 | 436 | 46 | 1259 | 1305 | 166
High | 1833 | 235 | 319 | 554 | 553 | 678 | 1231 | 48
Medium | 1478 | 39 | 335 | 374 | 72 | 998 | 1070 | 34
ShowStopper | 674 | 112 | 88 | 200 | 290 | 170 | 460 | 14
Unknown | 102 | 0 | 61 | 61 | 0 | 41 | 41 | 0
Total | 5994 | 425 | 1200 | 1625 | 961 | 3146 | 4107 | 262

## 5. Severity Distribution
Severity | Total Count | Open |  |  | Closed |  |  | Unmapped
|  | Client | Internal | Total | Client | Internal | Total
Not set | 5649 | 395 | 1114 | 1509 | 889 | 2999 | 3888 | 252
Sev-0 | 145 | 11 | 30 | 41 | 35 | 65 | 100 | 4
Sev-1 | 125 | 13 | 34 | 47 | 26 | 47 | 73 | 5
Sev-2 | 65 | 6 | 21 | 27 | 8 | 29 | 37 | 1
Sev-3 | 10 | 0 | 1 | 1 | 3 | 6 | 9 | 0
Total | 5994 | 425 | 1200 | 1625 | 961 | 3146 | 4107 | 262

## 6A. Component — Total, Open and
Component | Total Count | Open | Closed | Unmapped
(No component) | 1142 | 207 | 911 | 24
Admin Console | 1080 | 220 | 833 | 27
Connector | 593 | 227 | 230 | 136
Workspace | 324 | 84 | 234 | 6
Reports | 311 | 100 | 197 | 14
Identity Hub | 297 | 55 | 232 | 10
All modules | 276 | 141 | 129 | 6
Settings | 255 | 61 | 187 | 7
Password Vault | 236 | 59 | 173 | 4
Auto onboarding | 235 | 58 | 171 | 6
Digital Vault | 146 | 29 | 113 | 4
Workflow | 139 | 40 | 96 | 3
Session Monitoring | 121 | 30 | 88 | 3
Access Control | 111 | 31 | 76 | 4
Build and Deploy | 102 | 56 | 46 | 0
Identity Governance | 80 | 16 | 62 | 2
AGW | 77 | 40 | 37 | 0
Onboarding Engine | 75 | 6 | 63 | 6
Knight Analytics | 74 | 32 | 41 | 1
APEM | 59 | 25 | 33 | 1
Integration | 59 | 43 | 16 | 0
Alerts and Notification | 58 | 10 | 44 | 4
ACMO | 57 | 23 | 34 | 0
Web-gateway/proxy | 54 | 25 | 28 | 1
Application & Audit Logs | 49 | 18 | 27 | 4
CI-MAC Thick Client | 46 | 12 | 33 | 1
JML Engine | 46 | 19 | 23 | 4
PyCLI | 32 | 15 | 17 | 0
Linux Thick Client | 29 | 3 | 26 | 0
CI Kubernetes Infrastructure | 28 | 0 | 26 | 2
SIEM | 26 | 8 | 18 | 0
Discovery | 23 | 10 | 13 | 0
CI OVA | 23 | 2 | 19 | 2
Report/Dashboard | 21 | 6 | 15 | 0
PAMAPI | 19 | 7 | 9 | 3
PAM | 12 | 9 | 2 | 1
Browser Plugin | 11 | 6 | 5 | 0
RND | 10 | 8 | 2 | 0
RTSM | 8 | 2 | 6 | 0
MFA | 6 | 4 | 2 | 0
NHI CI Integration | 4 | 1 | 3 | 0
CI-Tag Management | 2 | 1 | 1 | 0
Total (distinct tickets) | 5994 | 1625 | 4107 | 262

## 6B. Component — Client and Inte
Component | Total Count | Open |  |  | Closed |  |  | Unmapped
|  | Client | Internal | Total | Client | Internal | Total
(No component) | 1142 | 1 | 206 | 207 | 3 | 908 | 911 | 24
Admin Console | 1080 | 75 | 145 | 220 | 225 | 608 | 833 | 27
Connector | 593 | 93 | 134 | 227 | 138 | 92 | 230 | 136
Workspace | 324 | 27 | 57 | 84 | 94 | 140 | 234 | 6
Reports | 311 | 14 | 86 | 100 | 48 | 149 | 197 | 14
Identity Hub | 297 | 20 | 35 | 55 | 49 | 183 | 232 | 10
All modules | 276 | 45 | 96 | 141 | 47 | 82 | 129 | 6
Settings | 255 | 5 | 56 | 61 | 25 | 162 | 187 | 7
Password Vault | 236 | 13 | 46 | 59 | 76 | 97 | 173 | 4
Auto onboarding | 235 | 12 | 46 | 58 | 49 | 122 | 171 | 6
Digital Vault | 146 | 20 | 9 | 29 | 25 | 88 | 113 | 4
Workflow | 139 | 13 | 27 | 40 | 19 | 77 | 96 | 3
Session Monitoring | 121 | 9 | 21 | 30 | 20 | 68 | 88 | 3
Access Control | 111 | 5 | 26 | 31 | 10 | 66 | 76 | 4
Build and Deploy | 102 | 1 | 55 | 56 | 6 | 40 | 46 | 0
Identity Governance | 80 | 5 | 11 | 16 | 10 | 52 | 62 | 2
AGW | 77 | 17 | 23 | 40 | 19 | 18 | 37 | 0
Onboarding Engine | 75 | 1 | 5 | 6 | 7 | 56 | 63 | 6
Knight Analytics | 74 | 1 | 31 | 32 | 0 | 41 | 41 | 1
APEM | 59 | 20 | 5 | 25 | 24 | 9 | 33 | 1
Integration | 59 | 9 | 34 | 43 | 11 | 5 | 16 | 0
Alerts and Notification | 58 | 8 | 2 | 10 | 26 | 18 | 44 | 4
ACMO | 57 | 4 | 19 | 23 | 14 | 20 | 34 | 0
Web-gateway/proxy | 54 | 12 | 13 | 25 | 16 | 12 | 28 | 1
Application & Audit Logs | 49 | 4 | 14 | 18 | 4 | 23 | 27 | 4
CI-MAC Thick Client | 46 | 4 | 8 | 12 | 9 | 24 | 33 | 1
JML Engine | 46 | 8 | 11 | 19 | 13 | 10 | 23 | 4
PyCLI | 32 | 0 | 15 | 15 | 0 | 17 | 17 | 0
Linux Thick Client | 29 | 2 | 1 | 3 | 14 | 12 | 26 | 0
CI Kubernetes Infrastructure | 28 | 0 | 0 | 0 | 0 | 26 | 26 | 2
SIEM | 26 | 7 | 1 | 8 | 13 | 5 | 18 | 0
Discovery | 23 | 0 | 10 | 10 | 0 | 13 | 13 | 0
CI OVA | 23 | 0 | 2 | 2 | 0 | 19 | 19 | 2
Report/Dashboard | 21 | 1 | 5 | 6 | 3 | 12 | 15 | 0
PAMAPI | 19 | 3 | 4 | 7 | 1 | 8 | 9 | 3
PAM | 12 | 3 | 6 | 9 | 2 | 0 | 2 | 1
Browser Plugin | 11 | 2 | 4 | 6 | 2 | 3 | 5 | 0
RND | 10 | 0 | 8 | 8 | 1 | 1 | 2 | 0
RTSM | 8 | 1 | 1 | 2 | 1 | 5 | 6 | 0
MFA | 6 | 2 | 2 | 4 | 2 | 0 | 2 | 0
NHI CI Integration | 4 | 0 | 1 | 1 | 0 | 3 | 3 | 0
CI-Tag Management | 2 | 1 | 0 | 1 | 1 | 0 | 1 | 0
Total (distinct tickets) | 5994 | 425 | 1200 | 1625 | 961 | 3146 | 4107 | 262

## 7. Top Reporters (Top 20)
Reporter | Count | % of Total
Pratik Dadasaheb Magdum | 285 | 4.8%
Mudabbir Hussain Bhat | 238 | 4%
shailesh sawant | 226 | 3.8%
Poonam Kulkarni | 214 | 3.6%
Vajreshwari Chalindrawar | 171 | 2.9%
Nazia Shaikh | 157 | 2.6%
Nadeem Naik | 143 | 2.4%
Avdhut Tad | 135 | 2.3%
Raj Shah | 121 | 2%
Chaitanya Pathak | 116 | 1.9%
Anand V | 104 | 1.7%
Harshad Prajapati | 103 | 1.7%
Keyur Solanki | 94 | 1.6%
Moiz Jawadwala | 80 | 1.3%
Heena Chaurasia | 80 | 1.3%
Sunil Ramesh Savale | 76 | 1.3%
Jeetendra Choudhary | 67 | 1.1%
Nishant Kumar Ghosh | 65 | 1.1%
Manish Shingre | 65 | 1.1%
pranay | 64 | 1.1%
Total (top 20 shown) | 2604 | 43.4%

## 8. Top Assignees (Top 20)
Assignee | Count | % of Total
Uttam Nayak | 822 | 13.7%
Vijayashree Shetty | 752 | 12.5%
Kalpesh Pusalkar | 531 | 8.9%
Akhil | 405 | 6.8%
Janam Bhavsar | 332 | 5.5%
Shrikant Shedekar | 161 | 2.7%
Param Sannakke | 140 | 2.3%
Arpita Upadhyay | 128 | 2.1%
Pinak Bhaskar Dere | 119 | 2%
Ronit Bose | 115 | 1.9%
Anand V | 103 | 1.7%
Parakh Shah | 88 | 1.5%
Heena Chaurasia | 87 | 1.5%
Jay Kawa | 74 | 1.2%
Moiz Jawadwala | 73 | 1.2%
Satyendra Pratap | 64 | 1.1%
Prashanth Reddy | 61 | 1%
balaji modalavalasa | 45 | 0.8%
Priyanshu Pandey | 42 | 0.7%
Jeetendra Choudhary | 41 | 0.7%
Total (top 20 shown) | 4183 | 69.8%

## 9. Monthly Creation Trend
Month | Count
2026-01 | 745
2026-02 | 736
2026-03 | 793
2026-04 | 634
2026-05 | 482
2026-06 | 506
2026-07 | 846
2026-08 | 734
2026-09 | 518
Total | 5994

## 10. Weekly Creation Trend
Week | Count
2026-W01 | 31
2026-W02 | 224
2026-W03 | 135
2026-W04 | 204
2026-W05 | 156
2026-W06 | 185
2026-W07 | 173
2026-W08 | 190
2026-W09 | 183
2026-W10 | 256
2026-W11 | 142
2026-W12 | 143
2026-W13 | 167
2026-W14 | 170
2026-W15 | 110
2026-W16 | 115
2026-W17 | 187
2026-W18 | 140
2026-W19 | 149
2026-W20 | 120
2026-W21 | 114
2026-W22 | 96
2026-W23 | 136
2026-W24 | 87
2026-W25 | 131
2026-W26 | 105
2026-W27 | 129
2026-W28 | 143
2026-W29 | 197
2026-W30 | 181
2026-W31 | 252
2026-W32 | 148
2026-W33 | 131
2026-W34 | 214
2026-W35 | 176
2026-W36 | 237
2026-W37 | 168
2026-W38 | 131
2026-W39 | 38
Total | 5994

## 11. Fix Version Distribution
Fix Version | Count
V10.12.000 | 579
V10.12.001 | 545
V10.12.003 | 283
V10.11.005 | 283
V10.11.003 | 274
V10.11.004 | 223
Sprint-Backlog | 155
V10.11.002 | 96
V10.11.001 | 77
V10.11.000 | 73
V10.11.003_HF3 | 67
V10.11.005_HF2 | 67
V10.11.004_HF | 43
V10.10.007 | 38
V10.10.007_HF5 | 31
V10.12.000_HF | 31
V10.10.007_HF3 | 30
V10.11.005_HF3 | 25
Future Release Tickets | 24
V10.11.005_HF1 | 17
V10.11.003_HF2 | 15
V10.10.007_HF2 | 13
V10.12.004 | 12
V10.12.002 | 11
v10.10.007_HF4 | 10
Mac Version 12.8.0.1 | 9
Mac Version 12.9.0.0 | 6
V10.10.004 | 6
V10.11.003_HF | 6
Backlog | 5
Total (top 30 shown) | 3054

## 12. Root Cause Analysis (RCA)
RCA | Count | % of Total
Not set | 1695 | 28.3%
Requests - Enhancement | 1219 | 20.3%
Code - Logic Issue | 897 | 15%
Others - Working as expected | 338 | 5.6%
Others - Resolved Issue | 260 | 4.3%
Analysis - Inadequate Technical Design | 216 | 3.6%
Environment - Misconfiguration | 194 | 3.2%
Code - UI/UX Issue | 140 | 2.3%
Insufficient Unit Test case | 108 | 1.8%
Code - Incorrect Standards | 101 | 1.7%
Documentation - Administrator / User Guide | 97 | 1.6%
Not a bug | 93 | 1.6%
Code - Code Merge | 75 | 1.3%
Environment - Non replicated | 67 | 1.1%
Code - Packaging Issue | 57 | 1%
Analysis - Incomplete Requirement | 50 | 0.8%
Code - Performance Issue | 46 | 0.8%
Requests - Information Request | 45 | 0.8%
Analysis - Inadequate Test Coverage | 44 | 0.7%
Code - Security Issue | 35 | 0.6%
Environment- Env unavailable | 34 | 0.6%
Environment - Network | 30 | 0.5%
Missing Code / DB Scripts | 25 | 0.4%
Requests - APEM Tool | 25 | 0.4%
Deployment Issue | 21 | 0.4%
Documentation - Deployment Guide Inadequate | 19 | 0.3%
Environment - Resource Unavailability | 15 | 0.3%
Requests - Script Request | 15 | 0.3%
Code - Ansible / OCI Issue | 10 | 0.2%
Environment - 3rd Party compatibility | 7 | 0.1%
Environment - Hardware failure | 5 | 0.1%
Code not checked-in | 4 | 0.1%
Miscommunication | 4 | 0.1%
Insufficient Data | 2 | 0%
Data Issue | 1 | 0%
Total | 5994 | 100%

## 13. Hosting Environment
Hosting Environment | Count | % of Total
Not set | 4454 | 74.3%
Windows | 1134 | 18.9%
RHEL | 287 | 4.8%
Kubernetes | 90 | 1.5%
Ubuntu | 29 | 0.5%
Total | 5994 | 100%

## 15. Sub-task Analysis
Ticket Kind | Count
Sub-tasks | 1443
Standalone (non-sub-task) | 4551
Total | 5994

## 15A. Top parent tickets by sub-
Parent Key | Sub-tasks
CI-16180 | 72
CI-16147 | 68
CI-22787 | 47
CI-23135 | 39
CI-20880 | 23
CI-20701 | 18
CI-22504 | 17
CI-22991 | 17
CI-20336 | 16
CI-22078 | 16
CI-21376 | 15
CI-23089 | 15
CI-23957 | 15
CI-13552 | 13
CI-20888 | 13
Total (top 15 shown) | 404

## 17. Open High-Priority Tickets
Key | Summary | Status | Priority | Assignee
CI-19093 | POC | HTI - frank's azure issue | Development Analysis | High
CI-19115 | Unity Bank V10 |  | IDHUB – “Perform Action API Not Working” error during Approval | Open
CI-19122 | Support for AGWA Setup and Configuration (Windows & Linux Components) | Internal | Awaiting Session | High
CI-19124 | Need support in deploying Web Gateway for | Internal CI_Test_OVA | Open | High
CI-19198 | Assistance Required for Password Rotation Issue in Marico POC | Awaiting Response | High | Shabaz Khan
CI-19223 | NBF |  | Unable to record the session error while in middle of session | Development Analysis
CI-19225 | Connector Request | Automate user SSO workflows between Easebuzz and Arcon CI | Business Analysis | High
CI-19232 | CLONE - FT- Kubernetes cluster with rbac | Open | High | Vijayashree Shetty
CI-19265 | Connector Request | Automate user SSO workflows between mtalkz and Arcon CI | Business Analysis | High
CI-19292 | PNB | Client Requirements for Reports, Dashboard, and Encryption | Open | High
CI-19306 | Unity Bank V10 |  | Enable editable selected attributes while raising a new asset | Open
CI-19316 | CLONE - Xceedance | CI-PAM | Issue with Report scheduler | Patch Shared
CI-19346 | Issue with auto onboarding of users from Entra ID and need support configure com | Open | High | Yashwanth Kumar H T
CI-19352 | Hero FinCorp SGW Issue: Connected host has failed to respond via SGW | Audit | ShowStopper | Moiz Jawadwala
CI-19385 | Reg: Issue with SFTP File transfer for Key based Server_ CI 10.10.007_v3 | Awaiting Session | High | srikanth.rendla
CI-19390 | User Attribute Field is not Populating in Asset. | Dev Review and Testing | High | Vijayashree Shetty
CI-19399 | AGWA Installation - Hero FinCorp POC | Open | ShowStopper | Abhishek Manikandan
CI-19411 | Performance Issue - CI Reports | Open | High | Arpita Upadhyay
CI-19413 | Performance Issues - Access, Onboarding & Reports | Open | High | Arpita Upadhyay
CI-19420 | JIO |  | NIC
CI-19430 | Admin Console | Incorrect Condition for Manual Reconciliation must be handled co | Development Analysis | High
CI-19454 | 169496 |  | JFSL
CI-19459 | Pycli | Helping COE team to understand and host PyCLI for OCI and OVA | Audit | High
CI-19543 | Develop a Test Connection API for ARCON CI Integration with third party IGA | Open | High | Satyendra Pratap
CI-19547 | CCIL |  | Need restricted Thick Client | Business Analysis
CI-19550 | PNB | Mac Id issue for Credential Access Logs | Development Analysis | ShowStopper
CI-19584 | Reconciliation Failed – Missing SAMAccountName / Contact Not Fetched | Awaiting Response | High | Wahid Shaikh
CI-19599 | Airtel B2B | Video Logs Background Notification Capture | Development Analysis | ShowStopper
CI-19614 | SIB | store logs in Temp location when main drive is offline | Business Analysis | ShowStopper
CI-19620 | JFL |  | CI 10.0.007

## 18. Unmapped Status Review
Status | Client | Internal | Total
Development Review | 53 | 117 | 170
Duplicate | 13 | 69 | 82
Pre Dev Audit | 1 | 3 | 4
Patch Tech Lead Review | 2 | 1 | 3
Patch Passed | 1 | 1 | 2
RCA/Resolution Review | 0 | 1 | 1
Total | 70 | 192 | 262

## 19. Unspecified Primary Client
Metric | Count
Open | 176
Closed | 621
Unmapped status | 28
Total | 825